## Week ending <<mm-dd-yy>>
<<Trantor Management System>>
Project Head	Vibhor
Week ending	27/07/12

Status of Last Week's Items
Planned Work		Action performed / Notes				Status
Provided User friendly customizable placeholder at template creation					closed
provided funchionality for to add new placeholder					closed
New logic for to import the data from CSV files for PDF generation					closed

Next Week's Target:
Planned Work					Status
Learn RSpec for two days					é
Implement test cases in protocal					é

Open Action Items (Depenedencies):
Description		Owner / Since		Impact
Description		Waiting On / Since		Impact
Description		Waiting On / Since		Impact

Open Risks/Issues :
Description				Probable Impact

Status Legend:
ê STOP HERE, THERE ARE ITEMS THAT NEED ATTENTION
è If the following are not addressed in time, we will be in CODE RED
é No Issues; all to plan or under control